Project Plan

5 hours per person per week * 4 people * 8 weeks = 160 hours to work with

| Tasks, durations, and dependencies |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task | Effort in hours | Dependencies |
| T1 | Create Customer | 6 |  |
| T2 | Create Newsagent | 5 |  |
| T3 | Create Delivery person | 4 |  |
| T4 | Create Order book | 6 |  |
| T5 | Create Publications | 4 |  |
| T6 | Create Delivery docket | 4 |  |
| T7 | Create Delivery area | 4 |  |
| T8 | Create Bill | 4 |  |
| T9 | Set up Database | 3 | T1 |
| T10 | Implementing database | 8 | T1-T9 |
| T11 | Set up GUI | 8 | T1-T8 |

| Allocation Table |  |  |  |  |
| --- | --- | --- | --- | --- |
| Week | Michael | Joseph | Luke | James |
| 1 | T9 | T2 | T4 | T1 |
| 2 | T10 | T2 | T4 | T1 |
| 3 | T10 | T2 | T4 | T1 |
| 4 | T10 | T3 | T5 | T6 |
| 5 | T10 | T3 | T5 | T6 |
| 6 | T10 | T11 | T7 | T8 |
| 7 | T10 | T11 | T7 | T8 |
| 8 | T10 | T11 | T11 | T10 |

Work Summary Plan – Week 1 – Week 2

- Create questions for Newsagents – Joseph

- Create project plan – James

- Work on software cycle justification – James

- Setup repository files – Luke

- Begin Excel Sheet for User Stories – Michael, Luke

Work Summary Plan – Week 3 – Week 4

- Finish User Stories and Acceptance Criteria for Entities – Michael, Luke

- Work on an overview of the project plan for dividing work – James

- Completed software lifecycle justification – James

- Implement Customer class – James

- Implement Newsagent class – Joseph

- Implement Order class – Luke

- Setting up database, start with linking customer – Michael

- Create Test Design Cases based off Acceptance Criteria – Joseph

Work Summary Plan – Week 5 – Week 6

- Create and execute Junit Testing following Test Driven Development for Customer – James

- Create and execute Junit Testing following Test Driven Development for Newsagent – Joseph

- Create and execute Junit Testing following Test Driven Development for Order – Luke

- Link the JDBC jar to the project so the database is connected – Michael

- Have Customer fully connected to the database with the necessary files and be able to create a new customer object completely from the Command Line and added to the database – James

- Have Newsagent fully connected to the database with the necessary files and be able to create a new newsagent object completely from the Command Line and added to the database – Joseph

- Have Order fully connected to the database with the necessary files and be able to create a new order object completely from the Command Line and added to the database – Luke

6 Week Project Plan – Divided into 3 Increments (2 weeks)

First Increment – Week 7 – Week 8

- Have all the statements and methods implemented so that the User can Create, Read, Update or Delete any Customer from the database – James

- Have all the statements and methods implemented so that the User can Create, Read, Update or Delete any Newsagent from the database – Joseph

- Have all the statements and methods implemented so that the User can Create, Read, Update or Delete any Order from the database – Luke

- Do a complete team peer review of each other’s work and look for things that can be improved – ALL

- Implement all parameters, TDD and connection to the database for Delivery Person – Joseph

- Implement all parameters, TDD and connection to the database for Publications – Luke

- Implement all parameters, TDD and connection to the database for Delivery Docket – James

- Implement all parameters, TDD and connection to the database for Delivery Area – James, Luke

- Implement all parameters, TDD and connection to the database for Bill – Joseph, Michael

Second Increment – Week 9 – Week 10

- Create GUI and base login system for Newsagent who can now manage any entity with its database with buttons and other actions on the GUI – Joseph

- Implement the order list for the delivery person who receives a new list of all publications to be delivered each day to each address and a system to check off if they have successfully delivered that publication – James

- For the Newsagent, create a summary list of what publications each customer successfully received that day – Luke

- Create and implement a stock system where it checks what items are in stock, send a message to the Newsagent when inventory of a certain item becomes low – Luke, Michael

Final Increment – Week 11 – Week 12

- Implement the calculated bill for a certain customer for that month and make sure the bill is included for the delivery person to deliver along side their publications – Joseph, James

- Implement where the customer will not be charged for the time they are away or put any publications on their deliver list if they are on holiday/away – Luke, Michael

- Implement a warning and reminder system for a scenario where the customer hasn’t paid their monthly bill and is sent the message along side their bill – James

- Create a notification for the Customer if a publication they ordered is not available/can’t be delivered – Joseph

- Make sure if a delivery is failed, it is added to the next day delivery docket – Luke

- Perform an entire review and testing (for bugs etc) of the Project and reflect on how it meets the speciation’s of the project – ALL